## WBS Spreadsheet
Milestone | Task ID | Task | Owner | Duration (days) | Notes
Establish a plant delivery and logistics plan | 1.1 | Source materials for packaging | fulfillment director
| 1.2 | Hire delivery drivers | HR
| 1.3 | Calculate the delivery fees | financial analyst
Select and install supply chain management software and equipment | 2.1 | Supervise vendor setup of inventory management and fulfillment software | inventory manager
| 2.2 | Supervise vendor installation of fulfillment equipment | fulfillment director
| 2.3 | Determine internal safety protocls for the equipment | quality assurance tester
Develop and launch an employee training programm | 3.1 | Develop training sessions | HR
| 3.2 | Train employees to use the new software and equipment | training manager
| 3.3 | Monitor progress and improve training process | training manager