## Template - Phase 1
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Plant Pals Marketing & Sales Strategy | director of product | marketing manager | marketing coordinator | copyrwriter | Head of sales | sales manager
PHASE 1
Task/Deliverable
Create a marketing plan for the new service | C | A | R | C | C | I
Write promotional copy | I | A | C | R | I | I
Design marketing assets (e.g., flyers, brochures, and online advertisements) | I | A | R | C | R | I
Create a customer outreach and on boarding plan | C | C | I | I | A | R