## Comm Plan Template
Project Plant Pals: Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Planning Meeting | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track | [link to meeting agenda and notes] | If needed, check in with manager about any high-level questions before meetings.
Software and Equipment Vendor | Planning Check-In | Weekly | Core Team: HR Specialist & Training Manager |  | In Person | Ask questions about the new software and equipment to create an effective training plan for Office Green's employees
Human Resources | Planning Meeting | Weekly | Core Team: HR Specialist |  | Phone Call | Project planning assistance; provide support during the training session
Facilities | Informational Update | Weekly | Core Team: Administrative Coordinator |  | Phone Call | Reserve rooms, spaces, and equipment needed for employee training
Print Shop | Planning Check-In | One time | Core Team: Administrative Coordinator |  | Email (from company address) | Coordinate on the printing and delivery of training manuals for employees
Office Green employees | Informational Update | One time | Project Manager |  | Phone Call | Communicate schedules, locations, and other necessary details to trainees
Office Green employees | Training | Weekly | Core Team: Training Manager |  |  | Train employees to use the supply chain management software and equipment
Office Green employees | Survey | One time | Core Team: Training Manager |  |  | Post-training survey
Your Manager | Status Update | Weekly | Project Manager |  | In Person | Update on event planning, ask questions, and get feedback
Senior Leaders: Director of Operations and the Director of Product (and CC your manager) | Status Update | One time | Project Manager |  | In Person | High-level information and general updates

## Comm Plan Template 2 (hidden)
Project Communication Plan
Project Title:
Project Manager:
Executive Sponsor:
Principal Stakeholder:
Date:
Deliverable Info (What) | Recipient(s) (Who) | Delivery Method(s) (How) | Schedule (When) | Who's Responsible? (Owner)
Project Information
Project Status
Agenda Minutes
Timeline Update
Project Updates Action Item Status
Project Risks

## Comm Plan Template 3 (hidden)
| Purpose | Medium | Frequency | Audience
Kickoff meeting
Project team meetings
Check-ins/ meeting recap
Project status meetings
UX design reviews